MOngolia EITI SECRETARIAT 2025 annual and progress report

## Brief introduction

In the early 2019, Mongolia EITI Secretariat was transferred from the Prime Minister’s office to the Ministry of Mining and Heavy Industry, and housed in this Ministry which is now called as Ministry of Industry and Mineral Resources.

MOF and World Bank agreed and concluded Grant agreement on Project to improve Transparency of extractive sector through implementing EITI in May 2022. The Project commenced in October and being implemented by EITI Secretariat, as Project implementing unit and completed by December 31st, 2023.

Starting from 1st of January of 2024, EITI Secretariat is operating under the State Budget funds and continued in 2025.

As result of these assistances Mongolia EITI activities had been normalized and Mongolia EITI produced a 16th of Report for 2021 by the end of 2022, 17th or Report for 2022 by the end of 2023 and 18th or Report for 2023 by the end of 2024, and 19th or Report-2024 by the end of 2025.

The Reports are available in Mongolian and English languages at Mongolia EITI website- http://www.eitimongolia.mn/p/33.

Mongolia EITI had planned to take following measures for 2025:

- To produce Mongolia EITI 2024 Report in compliance with requirements of EITI standard.

- Finalize draft law on transparency in Mineral Resources sector, and implement 33 recommendations given by Validation.

- Subnational EITI councils, which were reactivated in 2021 and now their activities have to be expanded and become more capable in terms of exchange of information and data, and stabilize their activities.

The following activities have been implemented within the scope of each output in 2025, namely:

## Output I. Commitment to the Extractive Industries Transparency Initiative standard maintained and improved

### Organization of EITI Reporting for 2024

It was estimated, 2105 mineral license and petroleum contract holding companies, or 926 companies with exploration license, 1346 companies with a production license, 167 companies with both licenses, and 7 companies with petroleum production sharing agreement have to produce EITI report for 2024 under new reporting templates.

In total 1010 companies have produced their EITI reports at E-portal, which was considered lowest number of reported companies.

The Secretariat has delivered official invitation with reporting template and password to the EITI E-reporting portal to the Government organizations such as 2 ministries and 7 agencies (such as taxation, mineral and petroleum, customs, professional inspection, state property, labor, social benefits, standard measurement, social insurance), Governors of 21 aimag, capital city and 9 districts to produce an EITI Report for 2024.

As result of these activities 5 agencies (like General taxation authorities, Mineral and Petroleum authorities, Customs office, Social benefits and service department, National Standard Measurement, its unit for probe), 3 districts and 15 aimags produced EITI report on revenues received from 972 companies.

### The procurement process for the 2024 EITI report

According to Work Plan for 2025, there would have to be the following activity related to the government procurement for the 2024 EITI report in the first quarter of 2025.

- establish an evaluation committee in the Ministry of Mining and Heavy Industry under related law.

- produce terms of reference of tender and tender documentations.

- Get approved terms of reference of tender and by MMHI.

The Evaluation Committee has been established in February 21st at MMHI, by order No/A/28 of the State Secretary of MMHI, and consisting of 2 representative from MMHI, 2 representative from NGOs, and one from the EITI Secretariat.

MMHI has approved the term of reference for consultancy services work for the production of Mongolian EITI 2024 or 19th Report.

The Selection and bidding process has started on 10th March with the publication of invitation of expression of interest both at the Government Procurement site www.tender.gov.mn.

As result of this selection work, partnership of SICA LLC and Growth Finance audit LLC was selected as consultant in April and contract was concluded on May 1st for MNT 109.000.000.0 and launched their work.

The inception seminar with task to finalize the scoping was organized in June 20th between Mongolia EITI Working Group and Secretariat and partnership of SICA LLC and Growth Finance audit LLC and it was agreed to the scoping and reconcile reports of 110 leading companies.

A draft report was submitted to MSG on October 24th within MSG meeting No.65 and approved finally by the National Council within meeting No.23 after discussions by members and additional work following and improving activities.

Within the follow-up activity of the Report official letters signed by the State Secretary of MIMR were delivered to Ministry of Environment, Climate change, General department of taxation, Mineral and Petroleum Authorities, department of State property policy and coordination and 42 companies, which refused to give answer to auditor, asked to study the Report and requested to take active actions with initiative, and give feedback within December.

The highlight of the achievement of Output I:  Mongolia EITI report 2024 or 19th was produced in timely manner.

## Output II. Enacting law on transparency in the extractive industry and creation legal framework

### Consultation on finalizing of Law on transparency in MRS

The Cabinet of Government established a working group for a drafting law on transparency in use of natural wealth in January 2025.

The Ministry of Justice and Internal affairs finalized the draft law of transparency in the extractive industries and draft is posted at website of MJIA for public feedback. https://mojha.gov.mn/content/651fbaff99e06106c641f63a

Ministry of Justice and Internal affairs is working the concept of that law. The Secretariat had met and submitted relevant materials about that law to MRs B.Zayabal, B.Uyanga, S.Zamira ans P.Munkhtulga.

The highlight of the progress of achievement of Output II: The draft law is produced, and prepared for the Cabinet hearing and expected to be enacted in 2026.

## Output III. Review of opportunities for better information dissemination and public monitoring of extractive sector activities conducted

### Communication with Subnational councils

The Secretariat had organized a consultation and training of all aimag Subnational EITI Councils on March 26th and April 24th in online format. 33 representatives of EITI subnational councils from 21 aimags and soums participated in this event, obtained information how to report for EITI under new EITI reporting system.

Information on the training, seminar, and communication

Training activities.

The Secretariat participated in a March 26 company meeting, operating in Khentii aimag, and made a presentation about EITI and company performance. Also, during that meeting, it briefed in details activities of EITI subnational councils and EITI Progress.

Moreover, the Secretariat participated in a June 6 company meeting, operating in Bayan-Ulgii aimag, and made a presentation about EITI and company performance. Also, during that meeting, it briefed in details activities of EITI subnational councils and EITI Progress.

The Secretariat participated in parallel panel discussions organized during Central and East regional responsible mining conferences in Darkhan-Ull and Khentii aimags, and answered questions.

Other communication activities

The Secretariat delegated 4 representatives from Company, CSO and Working group to peer exchange training program of Central Asia and Caucasus EITI implementing countries organized by EITI IS on January in Istanbul, Turkey, presented about ongoing EITI implementation and exchanged views.

The Secretariat delegated then state secretary of Ministry of Industry and Mineral resources to the Asia-Pacific meeting, jointly organized by OGP and EITI IS in March in Manila, Philippines, who briefed in details about Mongolian mining sector and EITI implementation.

Mongolia EITI nominated for membership representing Constitiency of Implementing countries Asia Pacifici region of EITI Board then state secretary of MIMR and he participated in elections for this membership along with Indonesian candidate and was selected as the member. However, he resigned from his original position because of new Government in Mongolia, then automatically he quitted EITI Board.

The Secretariat delegated 4 representatives from MIMR, Erdenes Mongol Company, CSO, and Working group to peer exchange training program and coordinators meeting of Central and South East Asia implementing countries organized by EITI IS on October in Jakarta, Indonesia, presented about ongoing EITI implementation and exchanged views.

The Secretariat delegated 2 representatives from State Registration and Secretariat to seminar on how to use data of Beneficial owners and peer exchange of Central Asia and Caucasus countries, jointly by Opening Extractives Program and EITI IS in November, Yerevan, made presentation on activities and learned some expertise.

The Secretariat jointly with Open Society forum a training on update of Contract website, invited relevant officials from EITI Subnational councils and aimag Governor’s office.

Under Opening Extractive Program jointly with EITI IS, consultancy work on pilot of verification of disclosed data of beneficial owners was concluded and independent consultant has been working, a report will be released soon.

The Secretariat made presentation on EITI implementation and Contract tranparency to members standing committee on industry of State Great Hural in June, and answered questions.

The Secretariat participated in Central and Eastern Regional Responsible mining conferences and Mining Week, and their paralel panle discussions.

The Secretariat met Butanes Government delegation at the Open Society forum in April, made presentation on ongoing EITI implementation in Mongolia.

Within EITI new requirement on prvention of corruption, contract was concluded with Integra Project of UN Development program on grant for funding training programs on developing Company internal rule to prevent corruption, based Mongolian national standard on prevention of corruption MNS 37001-2024. In accordance with this Contract, the Secretariat organized 3 trainings where representatives from 130 mining companies participated. The 7- person ad hoc group was established from these companies representatives and produced internal rule of company. One more training will be organized in 2026 and then the Program will be finalized.

The Secretariat jointlt NRGI and OSF organized the consultation of members of EITI National Council and Working Group in December of energy transition, and relevant activities in this regard, and at the end it was agreed to produce Road Map.

65th meeting of EITI working group

The 65th meeting of Mongolia EITI working was organized, during which the draft report of Mongolia EITI 2024 or 19th Reconciliation Report produced by partnership of SICA LLC and Growth finance audit LLC was discussed and approved for submission to the National Council meeting.

During the meeting, Secretariat submitted progress report of Mongolia EITI 2025 Work plan, and draft of Mongolia EITI 2026 Work plan and it was agreed to be submitted to the National Council meeting.

23rd meeting of National Council

23rd meeting of Mongolia EITI National Council was organized, during which the draft report of Mongolia EITI 2024 or 19th Reconciliation Report produced by partnership of SICA LLC and Growth finance audit LLC was discussed and National Council approved it.

During the meeting, Secretariat submitted progress report of Mongolia EITI 2025 Work plan, and draft of Mongolia EITI 2026 Work plan and a both were approved by the National Council

The highlight of the progress of achievement of Output III: Activities in communication and international cooperation had been conducted actively. Implementation is 100%.

Brief statement of the 2025 progress:

| Items | Output | Highlight of progress |
| --- | --- | --- |
| I | Commitment to the Extractive Industries Transparency Initiative standard maintained and improved. | - Procurement and Contract work for Mongolia EITI 2024 Reconciliation Report was done successfully in timely manner. - The Reconciliation Report covered reports of 110 mining companies and contextual information as per 2019 Standard annd finally approved by National Council. |
| II | Legislation to improve transparency in the extractive industry identified | The draft on transparency in extractive industries was updated and posted at the website of MJIA with link: https://mojha.gov.mn/contentList/62dfcd0a3982fa3c90f2a7da - New legal working group established at the Cabinet. - Some MPs of Parliament had been brief on law. |
| III | Review of opportunities for better information dissemination and public monitoring of extractive industry activities conducted. | - Online training for Central and local government officials, subnational councils were organized. - Participated in regional and aimag trainings. - All website and Facebook data are regularly updated. - Organized training on prevention of corruption under UNDP funding. - Pilot project on verification of disclosed data of beneficial owners was organized. |

## Mongolia has implemented EITI within its resources and opportunity in mediocre way.

## Planned Activities for 2026

The first priority is to produce Mongolia EITI 2025 or 20th Report in timely manner under new or 2023 Standard.

The second priority and focus of the 2026 Work Plan are to promote an enactment of the draft law on transparency in the extractive industries and prepare a smooth implementation of the law.

The third priority is to implement recommendations given by Mongolia EITI 2022 Validation.

Basic information from Mongolia EITI 2024 or 19th Reconciliation Report

The Mongolia EITI 2024 or 19th Reconciliation report endorsed the reconciliation of payments of 110 mining companies were 9.8 trillion MNT and revenue of the Government from these companies 9.78 billion in 2024.

As the result of initial reconciliation, the discrepancy was 810.5 billion MNT, and explanations and documentations were collected respective parties, and the adjustment was made. After the adjustment, the final discrepancy was amounted 22.5 billion MNT, which was concluded as unexplained discrepancy. This kind of conclusion reveals that quality of reporting is still not perfect, and there should a special attention to improve the reliability of data.

The total paid taxes of leading 20 companies represented the 96.9% of payment from the whole mining sector, but the majority belonged to top 5 companies out of them.  “Erdenes Tavantolgoi” LLC paid 3.38 trillion MNT of taxes, Erdenet SOE and Oyutolgoi LLC with foreign investment were next companies.

The share of extractive sector in GDP reached 27.3%, and remains one of biggest contributing sectors of the country.

The extractive sector creates still produces absolute majority of export revenue. The export price for coal decreased but it was not compensted even by the increase of export volume. From the other side, both copper concentrate price and volume have increased, and therefore, revenue increased the same time.

1365 contracts been published at the Contract transparency site www.iltodgeree.mn, but publication of contracts by state owned enterprises was not smooth, some procurement reports had not been published, and such cases are still common phenomenon.

The number of companies which disclosed data of beneficial owners decreased from 2023 by 14.2% and the fact that only 452 companies disclosed data is not the best indication.

Data of local authorities was incomplete, late and missing and was one of the factors affected on quality of the reconciliation.

The Mongolia EITI 2024 report is consisted of 6 chapters, 18 graphs, 11 figures, 76 tables, 38 annexes, totaly 374 pages of materials, the content is given below as follows. The Report and its annexes can be downloaded at this link https://www.eitimongolia.mn/p/68.

Content of 2024 Report

Chapter one. Introduction- 14, 1.1 Relevant infromation- 15, 1.2 Role of the independent administrator-compiler- 16, 1.3 Participants- 17, 1.4 Challenges- 17, 1.5 Acknowledgment -18 page.

Chapter two.  Reconciliation methodology and data coverage- 20, 2.1 Data coverage- 20, 2.1.1. Inception report process- 21, 2.1.2. Materiality of payments and revenues- 21,  2.2 Data collection methodology-24, 2.2.1. Forms used in the 2024 reconciliation- 25, 2.2.2. Level of disaggregation- 25, 2.3 Verification- 26, 2.3.1.	audit and verification environment in Mongolia -26, 2.3.2.EITI report verification process 27, 2.4 Accuracy of information- 28, 2.4.1. Reporting and response status- 28, 2.4.2. Ttransparency requirements for state participation- 30.

Chapter three. reconciliation results- 33, 3.1 Scope of reconciliation- 33, 3.2	Total Government revenue-	34, 3.2.1. Total revenue from the extractive industry in 2024- 34, 3.2.2. Reconciliation of government-reported revenue- 35, 3.2.3.	Comparison of government and company revenue streams after reconciliation-	35, 3.2.4. Summary of extractive sector revenue- 36, 3.3 Summary of initially reported flows- 37, 3.4 Initial unreconciled differences and non-reporting companies-	38, 3.5 Remaining unreconciled differences- 39, 3.6 Detailed reconciliation results- 42.

Chapter four. Overview of Mongolia’s extractive sector- 49, 4.1 Legal framework and fiscal policy overview (requirement 2.1)- 49, 4.1.1	Summary of legal framework changes- 49, 4.1.2 Fiscal policy and budget legislation-	 54,  4.2 Impact on the economy (requirement 3.1 and requirement 6.3)- 55, 4.2.1 Revenue collected (requirement 4.1)- 56, 4.2.2 Export revenue (requirement 3.3)- 58, 4.2.3 Production (requirement 3.2)-	61, 4.3	Mineral resources, utilization, and licensing policy- 65, 4.3.1 Overview of uranium-	65, 4.3.2 Strategic deposits- 66,  4.3.3 Artisanal and small-scale mining- 69, 4.3.4 licensing procedures for mineral exploration and extraction (requirements 2.2 and 2.3) -71, 4.4 Overview of the petroleum sector - 80, 4.4.1 Petroleum reserves and state involvement- 80, 4.4.2 Petroleum exploration and licensing (requirement 2.2.a) 81, 4.4.3 Production sharing agreements (requirement 2.4)- 83, 4.4.4 Petroleum production and economic indicators- 83, 4.4.5	Overview of natural gas sector -86, 4.5 State participation in the extractive sector (requirements 2.6, 4.5, 6.2)-	86, 4.5.1 Government and SOEs ownership in extractive companies and changes in ownership transfer- 87, 4.5.2 Financial relations and transactions between the Government and SOEs (requirements 2.6, 4.2, 4.5)- 89,  4.5.3 Public disclosure of soes’ financial statements (requirement 2.6.b)- 90, 4.5.1 Operations, asset utilization, procurement, and governance regulation of soes (eiti requirement 2.6.c)- 92, 4.5.2	Payments similar to budget expenditures- 95, 4.6	Budget process and revenue allocation-  96, 4.6.1 Revenue allocation- 96, 4.6.2 Cases of unrecorded or unreported local payments in the budget (requirement 4.6 and requirement 5.1)- 97, 4.6.3	Revenue management and expenditure (requirement 4.1 and requirement 4.7)- 99.

Chapter five. other matters- 102,  5.1	Ultimate beneficial ownership and its transparency (requirement 2.5)- 102,  5.2	Contract transparency- 104,  5.3 Investment in infrastructure and barter arrangements (requirement 4.3)- 106, 5.4 Transportation revenue (requirement 4.4)- 107, 5.5 Environmental rehabilitation information (requirement 6.4)- 109, 5.6 Electronic reporting system	- 112, 5.7 Water use information- 114, 5.8	Waste management information- 114, 5.9 Greenhouse gas emissions and project costs (requirements 3.4 and 4.10) - 115, 5.9.1 Oyu tolgoi llc greenhouse gas emissions- 115, 5.9.2	Oyu tolgoi llc project expenditures- 117, 5.9.3 Badrakh energy llc project expenditures- 118.

Chapter six. Implementation of recommendations -120, 6.1	Implementation of recommendations from previous consolidated reports- 120,  6.2 Action plan to implement the recommendations provided in the 2022 validation report- 128,  6.3	Recommendations on EITI reporting and its implementation- 135.

List of Graphs, page No

Graph 1. Payments and revenues received by government institutions, in million MNT- 22, Graph 2. GDP and Mining Sector Output and Share (at current prices), 2020–2024, in billion MNT- 56, Graph 3. Revenue collected from the mineral resources sector, 2020–2024, in billion MNT- 56, Graph 4. Revenue collected from the mineral resources sector by subsector, 2023–2024, in billion MNT- 57, Graph 5. Export performance of key mineral products, 2024- 58, Graph 6. Valuation and volume of mineral sector exports, 2024, in million USD- 59, Graph 7. Gold purchased by the Bank of Mongolia, 2020–2024 (kg)- 70, Graph 8. Gold purchased by the Bank of Mongolia by month, 2024 (kg)- 70, Graph 9. Number and total area of valid mineral licenses, thousand hectares, 2020–2024-	71, Graph 10. Petroleum product reserve balance by type, (tons), 2023–2024- 81, Graph 11. Petroleum production (thousand barrels), 2021-2024- 84, Graph 12. Crude oil exports (thousand barrels), 2021-2024- 85, Graph 14. Number of contracts published in the transparency database- 105, Graph 15. Balance of the environmental protection and rehabilitation guarantee account- 110, Graph 17. User guide for the EITI electronic reporting system- 113, Graph 18. Implementation of Recommendations by status and year- 120.

List of figures, page No

Figure 1. Process diagram of the Independent Administrator-Compiler’s role- 17, Figure 2. Sectors of companies included in the reconciliation report- 22, Figure 3. Stakeholders’ participation in the electronic reporting system- 25, Figure 4. EITI Report Verification and Preparation Process- 27, Figure 5. Locations of petroleum exploration and prospecting areas- 82, Figure 6. Petroleum export plan and performance, 2024- 84, Figure 7. Open information on state budget and audit activities- 100, Figure 8. Process of conducting the Baseline Environmental Assessment (BEA)- 111, Figure 9. Stages of the Environmental Management Plan- 112, Figure 10. Principles followed in developing the electronic reporting system- 113, Figure 11. Scope 1 and Scope 2 greenhouse gas emissions, 2024- 116.

List of table, page

Table 1. Government-reported revenues and number of companies, in billion MNT- 21, Table 2. 45 companies selected based on CSO recommendations- 23, Table 3. Information submitted by companies- 28, Table 4. Completion status of selected organizations’ forms- 29, Table 5. Companies that declined participation in the report- 31, Table 6. List of entities not registered in the electronic reporting system- 34, Table 7. Government revenue received, by institution, in million MNT- 34, Table 8. Reconciliation of government-reported revenue, in million MNT- 35, Table 9. Adjusted reconciliation of government and company revenue streams, in million MNT- 35, Table 10. Reconciliation results – Top 5 taxpayers, 2020–2024, in million MNT- 36, Table 11. Top 20 highest tax paying companies among the 110 companies included, in million MNT and percentage- 36, Table 12. Lowest 20 tax paying companies among the 110 companies included, in million MNT and percentage- 36, Table 13. Companies among the 110 that did not pay taxes in 2024- 37, Table 14. Initially reported payments, revenue flows, and adjustments, in million MNT- 38, Table 15. Summary of initial reported payments and revenues with adjustments, in million MNT- 38, Table 16. Unadjusted discrepancies, in million MNT- 38, Table 17. Remaining unreconciled differences by revenue stream, in million MNT- 39, Table 18. Remaining unreconciled differences by company, in million MNT- 40, Table 19. Main local-level revenue streams, in million MNT- 42, Table 20. Main national-level revenue streams, in million MNT- 42, Table 21.  National-level reconciliation results by revenue stream, in million MNT- 43, Table 22. Summary of legal amendments in the extractive sector in 2024- 50, Table 23. Summary of parliamentary resolutions related to the extractive sector in 2024- 50, Table 24. Summary of amendments to Government resolutions in the extractive sector in 2024- 51, Table 25. Budget legislation-	 54, Table 26. Budget revenue by sector, 2023–2024, in billion MNT- 57, Table 27. Average export prices of mineral products- 58, Table 28. Sales volume of entities included in the 2024 reconcliation report- 59, Table 29. Industrial sector production volume-	61, Table 30. Extraction volume of enterprises included in the 2024 reconciliation report-	62, Table 31. Extraction volume of enterprises included in the 2024 reconciliation report-	63, Table 32. Amendments to the Nuclear Energy Law in 2024- 65, Table 33. Active uranium exploration and mining licenses- 66, Table 34. Mineral deposits of strategic importance (Appendix 1 of the State Great Khural Resolution No. 27 of 2007)- 66, Table 35. Mineral deposits of strategic importance (Appendix 2 of the State Great Khural Resolution No. 27 of 2007)-	67, Table 36. Areas with approved conclusions for artisanal mineral extraction -71, Table 37. Number of mineral licenses with changes, by type, 2020–2024- 72, Table 38. Information on license fees, by the 110 companies covered, 2024	- 74, Table 39. Summary of the “Mongol Refinery” SOE Project	- 80, Table 40. Petroleum reserves of Mongolia, in million tons- 81, Table 41. Petroleum and natural gas sales revenue, 2023–2024-  84, Table 42. Petroleum and natural gas production value, 2023–2024	- 84, Table 43. Assessment of government agencies’ participation in EITI- 87, Table 44. Shareholder information of SOEs- 88, Table 45. Transparency of transactions between SOEs-	 90, Table 46. Compliance with reporting standards and transparency of SOEs- 91, Table 47. Transparency of financial statements of state-owned enterprises- 91, Table 48. Disclosure status of SOE audit reports- 92, Table 49. Disclosure status of internal regulations and charters of SOEs- 93, Table 50. Amendments and additions to laws and regulations related to the transparency of SOE procurement- 93, Table 51. Disclosure status on the Glass Accounts website- 94, Table 52. Transparency of procurement	- 94, Table 53. SOE Glass Accounts information- 95, Table 54. Updates in the 2024 budget process- 96, Table 55. Changes in loans to the extractive sector, in billion MNT- 97, Table 56. Amount of financial support approved for allocation to provinces in Mongolia’s 2024 state budget, in million MNT- 97, Table 57. Approved amount of 2024 revenue transfers to the Local Development Consolidated Fund, in million MNT- 98, Table 58. 2024 performance- 99, Table 59. Measures implemented by the EITI International Board on Beneficial Ownership- 102, Table 60. Ultimate beneficial owners of license-holding companies- 102, Table 61. Beneficial owners registered in the EITI electronic reporting system- 103, Table 62. Legal provisions related to contract disclosure- 104, Table 63. Contracts published in the database- 106, Table 64. Top 12 companies with the highest transportation revenues-	107, Table 65. Export freight transported by road, cumulative total- 107, Table 66. Export freight transported by rail, cumulative total- 108, Table 67. Total export freight, cumulative total- 109, Table 68. Summary of companies authorized to conduct land rehabilitation, 2024- 110, Table 69.  Water usage- 114, Table 70. TOP 10 companies paying the highest water use fees in 2024, in million MNT- 114, Table 71. Waste management data, м3- 114, Table 72. TOP 10 companies paying the highest waste management fees, thousand MNT-	115, Table 73. Oyu Tolgoi LLC project expenditures- 117, Table 74. Badrakh Energy LLC project expenditures, thousand MNT- 118, Table 75. Status of implementation of the Action Plan based on recommendations from the 2018, 2019, 2020, 2021, 2022, and 2023 EITI Mongolia Consolidated Reports — as of October 6, 2025	120, Table 76. Action plan to implement the recommendations provided in the 2022 Validation Report- 128.

Annexes, information

| Annex 1 | Information on companies covered in the 2024 Mongolia EITI Report |
| --- | --- |
| Annex 2 | Officials from government agencies who provided data for the reconciliation work |
| Annex 3 | Officials from local administrative organizations who provided data for the reconciliation work |
| Annex 4 | List of reporting templates sent to companies |
| Annex 5 | Reporting templates sent to government agencies |
| Annex 6 | Information submitted by companies |
| Annex 7 | Information submitted by government agencies |
| Annex 8 | Clarifications made for companies, by payment type |
| Annex 9 | Unexplained discrepancies in the initial reconciliation (by company) |
| Annex 10 | Initial reconciliation, corrections, and post-correction reconciliation (by company) |
| Annex 11 | Unexplained discrepancies, by company |
| Annex 12 | Major national revenue streams after reconciliation adjustments, by government data |
| Annex 13 | Major local revenue streams after reconciliation adjustments, by government data |
| Annex 14 | Employment information |
| Annex 15A | List of mining (exploitation) licenses (as of December 31, 2024) |
| Annex 15B | List of exploration licenses (as of December 31, 2024) |
| Annex 15C | List of newly issued licenses in 2024 |
| Annex 15D | List of exploration and mining licenses revoked in 2024 |
| Annex 15E | List of disqualified entities |
| Annex 16A | Coal production volume in 2024 |
| Annex 16B | Domestic and export sales volume and average (thousand tons) in 2024 |
| Annex 17 | Status of audited financial statements |
| Annex 18 | Composition of Boards of Directors |
| Annex 19A | Shareholder information |
| Annex 19B | Beneficial owners (individuals) |
| Annex 19C | Beneficial owners (legal entities) |
| Annex 19D | Dividends |
| Annex 20 | Information on contracts made with local administrative organizations |
| Annex 21 | Project-level information |
| Annex 22 | Environmental rehabilitation information submitted by companies |
| Annex 23A | Evaluation of company participation in EITI reconciliation |
| Annex 23B | Evaluation of government and state institutions’ participation in EITI |
| Annex 24A | Water usage information |
| Annex 24B | Water usage fees paid to the government (by company) |
| Annex 25 | Waste management information |
| Annex 26A | Information on electricity and steel ball usage |
| Annex 26B | Purchases of mineral raw materials and fuel consumption |
| Annex 26C | Information on food products used (meat, milk, dairy products) |
| Annex 26D | Information on occupational safety and hygiene products used |
| Annex 27 | Information on subcontractors |
| Annex 28 | Information from the Glass Accounts of state-owned enterprises |
| Annex 29 | Loan information of state-owned and private enterprises |
| Annex 30 | Resource data |
| Annex 31 | Information on impact zones |
| Annex 32 | Information on chemicals used by mineral processing companies |
| Annex 33 | Investments in infrastructure and barter agreements |
| Annex 34 | Information on mineral extraction, production, and sales (sales data) |
| Annex 35 | Transportation fees of state-owned and private enterprises |
| Annex 36 | List of contracts disclosed to the public |
| Annex 37 | List of contracts disclosed since 2024 |
| Annex 38 | 2024 revenue transfer information of the Local Development Consolidated Fund (thousand MNT) |

Compliance of requirements of EITI standard- Self assessment, May 27, 2026

| Component & module | EITI Requirement | Progress | Score |
| --- | --- | --- | --- |
| Outcomes and impact |  |  | 68/100 |
| Extra points | Effectiveness and sustainability indicators | 3.5 |  |
| Outcomes and impact | Work plan (#1.5) |  | 90 |
|  | Public debate (#7.1) |  | 50 |
|  | Data accessibility and open data (#7.2) |  | 80 |
|  | Recommendations from EITI (#7.3) |  | 60 |
|  | Outcomes & impact (#7.4) |  | 60 |
| Stakeholder engagement |  |  | 70/100 |
| Multi-stakeholder oversight | Government engagement (#1.1) |  | 60 |
|  | Industry engagement (#1.2) |  | 60 |
|  | Civil society engagement (#1.3) |  | 100 |
|  | MSG governance (#1.4) |  | 60 |
| Transparency |  |  | 57/100 |
| Overview of the extractive industries | Exploration data (#3.1) |  | 100 |
|  | Economic contribution (#6.3) |  | 90 |
| Legal and fiscal framework | Legal framework (#2.1) |  | 100 |
|  | Contracts (#2.4) |  | 90 |
|  | Environmental impact (#6.4) |  | - |
| Licenses | Contract and license allocations (#2.2) |  | 90 |
|  | License register (#2.3) |  | 100 |
| Ownership | Beneficial ownership (#2.5) |  | 100 |
| State participation | State participation (#2.6) |  | 60 |
|  | In-kind revenues (#4.2) |  | - |
|  | SOE transactions (#4.5) |  | 60 |
|  | SOE quasi-fiscal expenditures (#6.2) |  | 30 |
| Production and exports | Production data (#3.2) |  | 90 |
|  | Export data (#3.3) |  | 90 |
| Revenue collection | Comprehensiveness (#4.1) |  | 80 |
|  | Barter agreements (#4.3) |  | 30 |
|  | Transportation revenues (#4.4) |  | - |
|  | Disaggregation (#4.7) |  | 80 |
|  | Data timeliness (#4.8) |  | 100 |
|  | Data quality (#4.9) |  | 60 |
| Revenue management | Distribution of revenues (#5.1) |  | 50 |
|  | Revenue management & expenditures (#5.3) |  | - |
| Subnational contributions | Direct subnational payments (#4.6) |  | 60 |
|  | Subnational transfers (#5.2) |  | 60 |
|  | Social and environmental expenditures (#6.1) |  | 60 |
| New 2023 standard requirements | Project |  | 30 |
|  | Greenhouse emission |  | 30 |
|  | Information of water use |  | 60 |
|  | Rehabilitation information |  | 50 |
|  | Transportation information |  | 50 |
|  | Авилгаас урьдчилан сэргийлэх |  | 50 |
|  | Energy transition |  | 30 |
|  | Gender balance |  | 50 |
|  | Use of chemicals, zone of impact, loans of SOEs, subcontractors, operator, labor safety and sanitary products, meat, fuel, gaseline, energy, steel ball, waste disposal are become transparent. |  |  |
| Overall | It is under stable, relatively high level of implementation. |  |  |